## F-QMS-RM03A1
Risk and Opportunity Register
Dept: | Software
ID | Type (Risk/Opp.) | Description | Likelihood (L) | Impact | Level (L x C/B) | Planned Treatment / Action to Pursue | Responsibility | Due Date | Status
R-SW-001 | Risk | Critical or High-severity bugs occurring in production despite testing, potentially causing system downtime or data loss (as per SOP S-SW-BF-4 severity classification). | 2 (Medium/Possible) | 3 (Major) | 6 (High) | Treat: Rollback to the previous version, Follow the defined bug fix procedure (SOP S-SW-BF-4): immediate triage, war room for critical bugs, mandatory RCA, and deployment of hotfix. | Software Supervisor & Software Tester | Immediate upon occurrence | In Progress
R-SW-002 | Risk | Failed deployment or release causing service disruption during the maintenance window, despite pre-release validation (as per SOP S-SW-FR-2). | 2 (Medium/Possible) | 3 (Major) | 6 (High) | Treat: Execute the rollback plan (referenced in SOP S-SW-SD-1 and S-SW-FR-2). Monitor systems for 24h post-release using APM tools. Conduct post-release review. | Software Supervisor | Immediate upon occurrence | In Progress
R-SW-003 | Risk | Change Request implementation causing unintended side-effects or system instability due to complex dependencies (as per risk assessment in SOP S-SW-CR-3). | 2 (Medium/Possible) | 3 (Major) | 6 (High) | Treat: Mandatory top management approval for high-risk changes (SOP S-SW-CR-3). Deploy to staging first and execute comprehensive regression tests before production. | Business Analyst/Product Owner | Per Change Request schedule | In Progress
O-SW-001 | Opportunity | Structured Software Development Lifecycle (SOP S-SW-SD-1) provides a framework for consistent, high-quality software delivery through defined phases of planning, design, testing, and deployment. | 3 (High/Likely) | 3 (Major Benefit) | 9 (High) | Pursue: Ensure strict adherence to the SDLC for all projects. Use the defined documents (SRS,US, test plans) to maintain quality and traceability. | Software Manager & Feature Review Board, Business Analyst,UI/UX Desginer, Software Supervisor,Developer Team | Ongoing | In Progress
O-SW-002 | Opportunity | Controlled intake and prioritization of New Feature Requests (SOP S-SW-FR-2) ensures development efforts are aligned with business strategy and deliver maximum value. | 3 (High/Likely) | 3 (Major Benefit) | 9 (High) | Pursue: Leverage the Feature Review Board and TFS prioritization to build a strategic roadmap. Conduct bi-weekly demos to maintain stakeholder alignment. | Software Manager & Feature Review Board, Business Analyst,UI/UX Desginer, Software Supervisor,Developer Team | Ongoing | In Progress
O-SW-003 | Opportunity | Formal Software Service Catalog & SLA framework (SOP S-SW-SC-5) builds trust with subsidiaries by setting clear expectations, providing transparent prioritization, and enabling satisfaction tracking. | 3 (High/Likely) | 2 (Moderate Benefit) | 6 (High) | Pursue: Actively use the catalog to manage intake. Negotiate and meet SLAs to demonstrate reliability. Use post-implementation surveys to gauge success. | Shared Service Coordinator,Software Manager | Ongoing | In Progress

## F-QMS-RM-03A2
*Risk/Opportunity Level Matrix (Guide):
• Likelihood (L) & Consequence/Benefit (C/B) Scale: 1 (Low/Minor) to 3 (High/Major)
• Level = L x C/B: Low (1-2), Medium (3-5), High (6-9)
• Likelihood Scale Definitions
• 1 (Low/Rare): Unlikely to occur / Occurs < 1 per year.
2 (Medium/Possible): Could occur / Occurs 1-2 times per year.
3 (High/Likely): Expected to occur / Occurs > 2 times per year.
• Consequence/Benefit Scale Definitions 1-RISKS (Consequence):
1 (Minor): Minor disruption to QMS/service, minimal financial/reputational impact.
2 (Moderate): Moderate disruption, noticeable impact, some stakeholder dissatisfaction.
3 (Major): Significant QMS failure, major service impact, significant
2-OPPORTUNITIES (Benefit):
1 (Minor): Slight improvement in efficiency/satisfaction.
2 (Moderate): Noticeable improvement, tangible benefits.
3 (Major): Significant strategic advantage, major cost savings, or enhanced reputation.