## F-QMS-OP-01
`
QMS Objectives Register سجل أهداف نظام إدارة الجودة
Dept: | .................................... |  |  |  |  | ............................................... |  | الإدارة :
Obj. ID الكود | QMS Objective Description وصف الهدف | Measurable Target(s) قياسات الهدف | Plan to Achieve (What, Resources, Who, When) الخطة لتحقيق الهدف (ماذا , من , متي , كيف) | Responsible Person/Dept. مسؤل ( الشخص / الإدارة) | Monitoring Method & Frequency كيفية و وسيلة المتابعة |  | Target Completion Date ميعاد المتوقع لتحقيق الهدف | Status (Current) وصف الحالة
SW-OBJ-001 | Improve software quality by reducing post-release critical bugs. | Reduce the rate of Critical (P1) bugs reported post-production by 25% compared to the previous 12-month average. | (What) Strengthen code review standards; implement mandatory unit test coverage of 80% for new code. (Resources) Static code analysis tool; training on test-driven development. (Who) Software Supervisor & Dev Team. (When) Q4 2024 - Q1 2025 (Implementation), then ongoing. | Software Manager | Monthly review of bug severity reports (SOP SW-G4); Quarterly review of unit test coverage metrics. |  | December 31, 2025 (for 25% reduction target)
SW-OBJ-002 | Enhance stakeholder satisfaction with the Software Service Catalog process. | Achieve an average score of ≥ 4.0 (on a 5-point scale) in the quarterly post-implementation satisfaction survey. | (What) Formalize feedback loop: analyze survey results, assign action items, and communicate improvements back to subsidiaries. (Resources) Survey tool; dedicated meeting time. (Who) Shared Service Coordinator (Business Analyst/Software Supervisor). (When) Starting Q1 2025 and ongoing. | Software Manager | Quarterly review of survey scores and action item completion (SOP SW-S1). |  | Ongoing (First target review: March 31, 2025)
SW-OBJ-003 | Increase efficiency and predictability of the feature delivery process. | 1. Reduce the average time from Feature Request submission to Go/No-Go decision to ≤ 7 business days (from current ≤ 10). 2. Deliver 90% of prioritized features within the agreed-upon SLA timeline. | (What) 1. Streamline the Feasibility Assessment (SOP SW-G2) with clearer checklists. 2. Implement a visual release calendar and mandatory capacity planning for the Tech Team. (Resources) Project management tool (TFS) enhancements. (Who) Business Analyst, Software Supervisor, Software Manager. (When) Process updates in Q1 2025. | Software Manager | 1. Bi-weekly review of request lead times. 2. Monthly review of SLA compliance reports (SOP SW-S1, SW-S2). |  | June 30, 2025
SW-OBJ-004 | Ensure robust release management with zero unplanned major service disruptions. | 100% of scheduled releases will have a documented, tested rollback plan. Zero releases causing Severity 1 (system-down) incidents in the first 24 hours post-deployment. | What) Mandate the creation and dry-run testing of a rollback plan as part of the Pre-Release Validation (SOP SW-S2). (Resources) Staging environment for rollback tests. (Who) Software Supervisor, Systems Admin. (When) Implement for all releases starting Q1 2025. | Software Manager | Review of release documentation and post-release incident logs (SOP SW-S2). |  | Ongoing (Process compliance target: 100% from Q1 2025)
SW-OBJ-005 | Strengthen the Change Management process to minimize risk. | 100% of High & Critical Risk Change Requests (per Risk Assessment Matrix) are reviewed and approved by the CAB before implementation. | (What) Formalize the Risk Assessment Matrix criteria and CAB approval workflow within the Change Request Form (SOP SW-G3). (Resources) Updated forms; CAB charter. (Who) Business Analyst (for assessment), CAB Chairman (SW Manager). (When) Process update in Q1 2025. | Software Manager | Monthly audit of Change Request records against the CAB meeting minutes. |  | March 31, 2025 (for process implementation)