## F-QMS-RM-01 A
Context Register (Internal & External Issues)
Dept:
Issue ID | Internal/External Issue Description | Source / Category | Potential Impact on QMS (Positive/Negative) | Monitoring / Review Method | Responsible
EXT-SW-001 | External: Rapidly evolving cybersecurity threats and data privacy regulations (e.g., local data laws) affecting software architecture and deployment practices. | External - Legal / Regulatory / Technological | Negative: Non-compliance risk, security breaches, and reputational damage. Positive: Forces modernization of security practices, potentially becoming a market differentiator. | Quarterly review of security advisories and regulatory updates; Annual security audit. | Software Manager & IT Team
EXT-SW-002 | External: Increasingly diverse and demanding requirements from AKG subsidiaries, leading to scope creep and challenges in prioritization. | External - Market / Stakeholders | Negative: Strain on resources, potential dilution of product quality, and missed deadlines. Positive: Demonstrates high demand and trust in the software unit's capabilities. | Regular (Bi-weekly/Monthly) priority alignment meetings with subsidiary liaisons; Review of SLA compliance. | Software Manager & Shared Service Coordinator
EXT-SW-003 | External: Dependency on specific technologies, frameworks, or vendors (e.g., TFS, specific CI/CD tools) that may become obsolete, unsupported, or change licensing terms. | External - Technological / Supply Chain | Negative: Technical debt, increased costs, and potential disruption to development pipeline. | Annual technology stack review; Monitoring of vendor roadmaps and industry trends. | Software Supervisor & Systems Admin
INT-STR-SW-001 | Internal Strength: Existence of a comprehensive, documented Software Development Lifecycle (SDLC) procedure (SOP SW-G1) covering planning, development, testing, deployment, and maintenance. | Internal - Process Maturity / Documentation | Positive: Provides a standardized, repeatable framework for delivering software, ensuring consistency, quality control, and traceability throughout the project lifecycle. | Regular project audits against SOP SW-G1; Review of lifecycle phase completion metrics. | Software Manager
INT-STR-SW-002 | Internal Strength: Defined and severity-based procedure for Bug Management (SOP SW-G4) with clear steps for reporting, triage, fixing, validation, and Root Cause Analysis (RCA). | Internal - Quality Assurance / Problem Resolution | Positive: Enables rapid response to defects, minimizes business disruption, and includes a proactive element (RCA) to drive long-term quality improvement. | Monitor bug resolution times by severity; Review RCA reports and implemented preventive actions. | Software Supervisor
INT-STR-SW-004 | Internal Strength: Implementation of a formal Software Service Catalog (unclear) and SLA framework (SOP SW-S1) for managing requests from subsidiaries. | Internal - Customer Focus / Service Management | Positive: Professionalizes intake, sets clear expectations with internal customers (subsidiaries), and provides a basis for measuring service performance and satisfaction. | Track SLA compliance metrics; Analyze post-implementation survey results. | Shared Service Coordinator
| Frequent relocation of the development team causing interruptions in workflow and reduced productivity. | Internal – Environment / Resources | Negative: Disruptions can slow delivery timelines, reduce focus, and increase error rates. | Monitor team productivity metrics, sprint velocity changes, and employee feedback surveys. | Software Manager
| Cloudflare issue caused AI-related features to stop functioning temporarily. | External – Technology / Vendor Dependency | Negative: Service outages affect development | Monitor uptime dashboards, vendor status pages, and incident reports. | Software Manager
| New bugs introduced during regression testing while fixing existing issues, leading to repeated cycles of defect creation and resolution. | Internal – Quality / Development Process | Negative: Causes delays in releases, increases testing workload, reduces stability, and impacts customer confidence. Positive: Improved test coverage and defect detection over time. | Track defect origin analysis, regression test reports, bug trends, root-cause analysis (RCA), and sprint retrospectives. | Technical Team
| Microsoft ended support for .NET 7, requiring a full upgrade of the system to .NET 8. | External – Technology / Compliance | Negative: Forced upgrades create unplanned workload, risk of breaking changes, and require significant testing. Positive: Upgrading improves performance, security, and long-term support stability. | Review Microsoft lifecycle announcements, dependency audits, upgrade planning and tracking. | Software Manager/ Team Supervisor
| Major refactoring of the entire codebase due to adopting a new backend architecture and frontend UI framework. Significant logic restructuring was required. | Internal – Technology / Architecture | Negative: Large refactors increase risk of defects, introduce instability, and delay ongoing development. Positive: Improved architecture enhances scalability, maintainability, and long-term performance. | Track refactoring progress, code review findings, regression testing results, and defect trends during sprints. | Software Manager/ Team Supervisor/ Technical Team