| Document Title | Document Code | Document Type | Issue No | Sop No. |
| --- | --- | --- | --- | --- |
| New Feature Request | S-SW-FR | SOP | 01 | 2 |
| Issue Date | Effective Date | Copy No. | Revision No. |  |
| 01/10/2025 | 01/10/2025 | Master | 0 |  |

Purpose
Standardize the intake, evaluation, development, and deployment of new feature requests to ensure alignment with business goals, efficient resource utilization, and stakeholder satisfaction.

Procedure & Flow

Step 1: Request Intake

- Action:

  - Stakeholder submits request via Feature Request Portal or form (business case, expected outcomes, mockups).

  - Required fields: Priority (P0 > P3), impacted subsidiaries.

- Roles:

  - Subsidiary Liaison/Internal Stakeholder: Logs request.

  - Shared Service Coordinator(Technical Team Lead): Assigns tracking ID.

Step 2: Technical Feasibility & Scoping

- Action:

  - Technical Team (Team Lead, Business Analyst, Developers, UI/UX) assesses:

    - Technical complexity

    - Integration points

    - Resource requirements

- Output: High-Level Design (HLD) document.

- Roles:

  - Team Lead: Leads assessment.

  - Software Manager: Approves HLD.

- Timeline: ≤5 business days.

Step 3: Prioritization & Roadmap Alignment

- Action:

  - Review by Feature Review Board (SW Manager, Product Owner, Subsidiary Rep).

  - Prioritize using RICE framework (Reach, Impact, Confidence, Effort).

- Roles:

  - SW Manager: Final prioritization.

Step 4: Agile Development

- Action:

  - Break into user stories; assign to sprints.

  - Bi-weekly stakeholder demos.

- Roles:

  - Dev Team: Implements features.

  - Tester Engineer: Continuous validation.

Step 5: Release & Adoption Tracking

- Action:

  - Deploy via phased rollout (canary release).

  - Monitor adoption via usage analytics.

- Roles:

  - Full Stack Engineer: Manages deployment.

  - BI Team (if any): Tracks adoption metrics

Documents & Records

- Feature Request Form by Shared Service Coordinator

- High-Level Design (HLD) by technical team Lead

- RICE Prioritization Matrix by SW Manager

Forms

| Form Name | Form Code |
| --- | --- |
| SERVICE REQUEST FORM | F-SW-FR/01 |

Revision History

| Rev No | Rev Date | Issue No | Issue Date | Description of Change | Approved By |
| --- | --- | --- | --- | --- | --- |
| 0 | 01-10-2025 | 01 | 01-10-2025 | Initial Issue |  |